## Android App
NSTR Patrol - Android App Work Plan (REAL STATUS)
ID | Module / Area | Sub-Item / Functionality | Status | Completion % | Est. Remaining (hrs) | Notes / Remarks
A01 | Build & Config | AGP namespace + applicationId | Done | 100 | 0 | Verified aligned.
A02 | Build & Config | Centralized tunables (AppConfig) | Done | 100 | 0 | All consts in AppConfig.kt.
A03 | Build & Config | Release signing + CI pipeline | Partial | 40 | 6 | release minify on; signing/CI not confirmed.
A04 | Build & Config | API base URL build config | Done | 100 | 0 | -PapiBaseUrl; default 10.0.2.2.
B01 | Auth & Device | Login (POST /api/auth/login) | Done | 100 | 1 | Works.
B02 | Auth & Device | Auth session / token storage | Done | 100 | 1 | AuthSession.
B03 | Auth & Device | Device registration (POST /api/devices) | Done | 100 | 0 | On login.
B04 | Auth & Device | Network client (no retry/timeout) | Partial | 70 | 4 | OkHttp exists; no resilience layer.
C01 | Patrol Lifecycle | PatrolStartScreen UI | Done | 100 | 1 | UI + reliably persists local session (team details) so they appear in PatrolReportScreen; creates backend patrol at start.
C02 | Patrol Lifecycle | PatrolTimer local elapsed clock | Done | 100 | 0 | Local monotonic clock.
C03 | Patrol Lifecycle | CREATE PATROL on backend | In Progress | 75 | 3 | Client-generated patrolId registered at start; PatrolStartScreen calls api.createPatrol; backend accepts client id (forestId resolved server-side). Requires >=1 forest row in DB.
C04 | Patrol Lifecycle | Record patrol END TIME + status | Done | 100 | 0 | End time + stats persisted on stop and POSTed to /api/patrols/:id/complete. End time now anchored to the real patrol stop time (trusted timer) instead of the last GPS sample, so duration reflects true start->end (fixes collapsed ~2-min durations). End Patrol button now hides immediately on confirm and navigation is not blocked by sync errors.
C05 | Patrol Lifecycle | AllPatrolsScreen real data | In Progress | 90 | 1 | AllPatrolsScreen now fetches GET /api/patrols (source of truth) and shows local PENDING sessions; static mock list removed. Dedupe via syncStatus.
C06 | Patrol Lifecycle | PatrolReportScreen (server report) | In Progress | 70 | 2 | Falls back to GET /api/patrols/:id when no local session; renders summary/timing/team. Team details + duration now correct (local session persistence + real end time fixed this session). Route map still local-only (no GET points endpoint).
C07 | Patrol Lifecycle | Server-side patrol tracking | In Progress | 40 | 5 | Depends on C03/C04+D07; backend tracking now reachable via sync upload.
D01 | Telemetry & Tracking | GPS capture local | Done | 100 | 1 | GpsTelemetryManager.
D02 | Telemetry & Tracking | Persist patrol points locally (Room) | Done | 100 | 1 | Every 30s.
D03 | Telemetry & Tracking | Sensor readings local | Done | 100 | 2 | Recorded locally.
D04 | Telemetry & Tracking | Movement classification | Done | 100 | 0 | PatrolsAppScreen lists server patrols; PatrolReportScreen loads detail + stats + server route points.
D05 | Telemetry & Tracking | Activity summary / metrics | Done | 100 | 1 | Local.
D06 | Telemetry & Tracking | Time integrity / tamper | Done | 100 | 1 | TrustedTimeManager.
D07 | Telemetry & Tracking | TELEMETRY SYNC UPLOAD | In Progress | 70 | 6 | SyncManager.syncNow pushes PENDING patrol rows + points + readings via /api/sync/upload. Triggered on start, every 30s while running, and on stop.
D08 | Telemetry & Tracking | Offline sync queue / WorkManager | In Progress | 60 | 4 | Sync is mobile->server only, connectivity-driven: ConnectivityObserver fires SyncManager.syncNow on (re)connect plus on start/stop. No network/server polling. WorkManager background scheduled sync still TODO.
D09 | Telemetry & Tracking | Register server patrolId before sync | Done | 100 | 0 | patrolId generated client-side at start and registered before tracking begins.
D10 | Telemetry & Tracking | Live telemetry to server | Pending | 0 | 6 | Server upload works when connectivity is gained (event-driven); not streamed continuously yet. Depends on D07 (done).
E01 | Maps | Offline MBTiles atlas + tile server | Done | 100 | 1 | Fetches from backend.
E02 | Maps | GIS beats + compartments layers | Done | 100 | 1 | Real backend data.
E03 | Maps | Incident / sighting markers | Done | 100 | 1 | From GIS.
E04 | Maps | Live patrol track (line + dots) | Done | 100 | 1 | Added this session.
E05 | Maps | Satellite deep-zoom basemap | Done | 100 | 2 | Esri; maxZoom 19.
E06 | Maps | Layer controls + legend | Done | 100 | 1
E07 | Maps | Fullscreen map mode | Done | 100 | 0
E08 | Maps | Connect map track to live server | In Progress | 60 | 2 | Local track already shown on map; now synced to server via D07.
F01 | Incident / Reporting | Reporting screens UI | Done | 100 | 0 | Reporting screens (HumanImpact/AnimalMortality/Sighting/WaterSource/QuickCapture) now capture input and submit via submitIncident().
F02 | Incident / Reporting | Incident + QuickCapture SYNC UPLOAD | In Progress | 80 | 3 | Local IncidentEntity + DAO + SyncManager.syncIncidents pushes pending incidents via /api/sync/upload (entity 'incidents'). All 5 reporting screens persist locally and sync on connectivity. Image upload (F04) still pending.
F03 | Incident / Reporting | Image persistent storage w/ timestamp | Pending | 0 | 8 | MISSING.
F04 | Incident / Reporting | Image upload API + send | Pending | 0 | 10 | No multipart upload in mobile.
F05 | Incident / Reporting | Reports dynamic data + dropdown fixes | Pending | 0 | 8 | STATIC + dropdown bugs.
G01 | SOS | SosScreen UI | Partial | 50 | 2 | UI exists; no POST.
G02 | SOS | SOS submit to backend | Pending | 0 | 6 | Backend ready; mobile never calls.
G03 | SOS | Emergency contacts fetch | Pending | 0 | 3 | MISSING.
G04 | SOS | Push notifications (FCM) | Done | 100 | 0 | PatrolReportScreen now draws route from server points for patrols recorded elsewhere (GET /api/patrols/:id/points).
H01 | Diagnostics & Settings | GpsDiagnosticsScreen | Done | 100 | 1 | Local.
H02 | Diagnostics & Settings | SettingsScreen existing options | Partial | 60 | 3 | UI; wiring to verify.
H03 | Diagnostics & Settings | Settings functional options (offline map etc.) | Pending | 0 | 12 | MISSING.
H04 | Diagnostics & Settings | LogsScreen | Done | 100 | 0 | Local logs.
I01 | Navigation & UX | Bottom navigation | Done | 100 | 1
I02 | Navigation & UX | ActivePatrolOverlay | Done | 100 | 0
I03 | Navigation & UX | DASHBOARD real data (no pre-assigned) | Pending | 0 | 8 | Rework needed.
I04 | Navigation & UX | Theme / branding | Partial | 70 | 3 | Spot-check.
J01 | QA & Release | On-device build verification | Done | 100 | 0 | compileDebugKotlin passing.
J02 | QA & Release | E2E patrol + sync test | Pending | 0 | 10 | Blocked C03/D07.
J03 | QA & Release | Field / offline test | Pending | 0 | 12 | Real-device forest test.
K01 | Localization & i18n | In-app language selector (Settings -> Language) | Done | 100 | 0 | Settings -> Language offers English, Hindi, Telugu, Bengali; runtime locale switch via ContextWrapper; bottom-nav labels localized through nav_* string resources.
K02 | Localization & i18n | Translated string resources (hi/te/bn) | Partial | 70 | 3 | nav_*, settings and core strings translated; full catalog coverage still pending.

## Backend
NSTR Patrol - Backend Work Plan (verified from code)
ID | Module / Area | Sub-Item / Functionality | Status | Completion % | Est. Remaining (hrs) | Notes / Remarks
B-INF-01 | Infra & Config | Express app + helmet + cors + json | Done | 100 | 1 | helmet+cors() enabled.
B-INF-02 | Infra & Config | Env config (env.ts) | Done | 100 | 0 | Typed env.
B-INF-03 | Infra & Config | Prisma client + DB health check | Done | 100 | 0
B-INF-04 | Infra & Config | Schema migration to patrolId (code) | Done | 100 | 0 | PatrolAssignment removed.
B-INF-05 | Infra & Config | Migration DEPLOYED to DB (migrate deploy) | Pending | 0 | 2 | Schema changed but not applied to a live DB yet.
B-INF-06 | Infra & Config | CORS origin restriction (not open-to-all) | Pending | 0 | 2 | cors() currently allows any origin.
B-INF-07 | Infra & Config | Rate limiting / compression | Pending | 0 | 3 | None configured.
B-INF-08 | Infra & Config | Structured logging / monitoring | Partial | 60 | 3 | logger middleware exists; no metrics.
B-INF-09 | Infra & Config | Automated tests (jest) | Partial | 30 | 10 | Only 2 smoke tests (app info, health). No route/integration tests.
B-AU-01 | Auth & Users | Login + JWT access/refresh | Done | 100 | 1
B-AU-02 | Auth & Users | Register (admin/user) | Done | 100 | 1
B-AU-03 | Auth & Users | /me, logout, password change | Done | 100 | 1
B-AU-04 | Auth & Users | Role-based access (requireAuth/Admin) | Done | 100 | 0
B-AU-05 | Auth & Users | Users CRUD (list/get/update/activate/deactivate/verify) | Done | 100 | 2
B-AU-06 | Auth & Users | Devices register | Done | 100 | 0
B-GI-01 | Forests & GIS | Forests CRUD | Done | 100 | 1
B-GI-02 | Forests & GIS | Beats CRUD + import | Done | 100 | 1
B-GI-03 | Forests & GIS | Compartments CRUD + import | Done | 100 | 1
B-GI-04 | Forests & GIS | Grids + boundaries | Done | 100 | 1
B-GI-05 | Forests & GIS | Serve beats/compartments GeoJSON | Done | 100 | 1
B-GI-06 | Forests & GIS | MBTiles asset serve + upload | Done | 100 | 1
B-GI-07 | Forests & GIS | Map routes CRUD | Done | 100 | 1
B-PA-01 | Patrols | Create patrol | Done | 100 | 1
B-PA-02 | Patrols | List / get patrols (filters) | Done | 100 | 1
B-PA-03 | Patrols | Start patrol (status ACTIVE + startedAt) | Done | 100 | 1 | Backend ready; mobile never calls.
B-PA-04 | Patrols | Complete patrol (endedAt + status) | Done | 100 | 1 | Backend ready; mobile never calls.
B-PA-05 | Patrols | Patrol aggregates (distance/metrics) | Done | 100 | 1
B-PA-06 | Patrols | Grids / boundaries per patrol | Done | 100 | 1
B-TE-01 | Telemetry | Ingest patrol points (POST /api/telemetry) | Done | 100 | 2 | Accepts bearing etc.
B-TE-02 | Telemetry | Ingest sensor readings (step/baro/accel/gyro/mag) | Done | 100 | 2
B-TE-03 | Telemetry | Ingest activity segments / coverage / integrity | Done | 100 | 2
B-TE-04 | Telemetry | Geo utilities (lib/geo) | Done | 100 | 0
B-IN-01 | Incidents | Create incident (patrolId) | Done | 100 | 1
B-IN-02 | Incidents | List / get incidents (filters) | Done | 100 | 1
B-IN-03 | Incidents | Incident photo upload endpoint | Done | 100 | 1
B-SY-01 | Sync | Batch upload (all models) | Done | 100 | 2
B-SY-02 | Sync | Changes feed (since) | Done | 100 | 1
B-SY-03 | Sync | Status (pending counts) | Done | 100 | 1
B-SY-04 | Sync | Sync logs | Done | 100 | 1
B-SO-01 | SOS & Alerts | Create SOS incident | Done | 100 | 1
B-SO-02 | SOS & Alerts | Emergency contacts (GET) | Done | 100 | 1
B-SO-03 | SOS & Alerts | Alerts feed (tamper/coverage) | Done | 100 | 1
B-SO-04 | SOS & Alerts | Push notification DELIVERY | Pending | 0 | 12 | Wiring pending s10; no FCM provider.
B-SO-05 | SOS & Alerts | FCM / push provider integration | Pending | 0 | 10
B-UP-01 | Uploads & Storage | Multipart upload (multer) + storeBuffer | Done | 100 | 1 | Local filesystem.
B-UP-02 | Uploads & Storage | Serve asset by key | Done | 100 | 1
B-UP-03 | Uploads & Storage | Object storage (S3/cloud) for prod | Pending | 0 | 8 | Local FS only; needs volume/object store.
B-UP-04 | Uploads & Storage | Image processing / thumbnails | Pending | 0 | 6
B-OP-01 | Options / Config | Key-value options GET/PUT | Done | 100 | 0
B-IN-01b | Integration Reality | Mobile uses auth/device/GIS endpoints | Partial | 70 | 2 | These are the only ones wired in mobile.
B-IN-02b | Integration Reality | Mobile uses patrol/telemetry/incident/sos/image endpoints | Pending | 0 | 4 | Endpoints exist & compile; mobile never calls them.
B-IN-03b | Integration Reality | End-to-end test with real mobile client | Pending | 0 | 12 | Blocked until mobile integrates.

## Web
NSTR Patrol - Web Work Plan
SNO | TYPE | TITLE | DESCRIPTION | MODULE/AREA | EST. EFFORTS | START DATE | END DATE | STATUS | PROGRESS % | BLOCKER | EXTERNAL DEPENDENCY | RESOLUTION / FIX DETAILS | VERIFIED ON | REMARKS
1 | Feature | Admin module removal from frontend | Deleted 7 admin pages (dashboard, users, roles, master-data, audit-logs, settings, app-releases), mock data, types, services, nav entry, adapters, API methods. Removed 8 API endpoints. Zero /admin routes remaining. | Admin Module | 4h | 2026-08-25 | 2026-08-25 | Completed | 100% |  |  | tsc clean, eslint 0 errors, next build success, 34 routes verified | 2026-08-25 | All admin code preserved in git history
2 | Feature | Dashboard page commenting - disabled with placeholder | Commented out entire dashboard page code (KPI cards, patrol mix, authorizations, recent activity). Replaced with placeholder component showing 'Dashboard is currently disabled'. Removed dashboard from sidebar nav. All original code preserved in comments for future re-enable. | Dashboard | 2h | 2026-08-25 | 2026-08-25 | Completed | 100% |  |  | Commented code preserves functionality; nav entry removed; build passes | 2026-08-25 | Dashboard disabled due to data duplication across modules
3 | Feature | Patrols module UI redesign - table-based view | Replaced dashboard-style patrols page with clean data table (14 columns). Added 8 filters (Status, Ranger, Division, Sub-Div, Range, Beat, Method, Date Range). Dependent filter chain: Division > Sub-Div > Range > Beat. Client-side pagination (PAGE_SIZE=15), column sorting, search field. Empty/error states. | Patrols Module | 6h | 2026-08-25 | 2026-08-25 | Completed | 100% |  |  | tsc clean, next build success. DataTable column header type upgraded string > ReactNode for sortable JSX headers | 2026-08-25 | Replaces old dashboard-style patrols view
4 | Bug Fix | Added subDivision field to Patrol type and adapter | Patrol type was missing subDivision field causing compilation errors when backend returns geography.subDivision. Added field to Patrol interface in types.ts, updated patrolFromApi adapter to map geography.subDivision, added subDivision to all 21 mock patrol objects. | Patrols / Types | 1h | 2026-08-25 | 2026-08-25 | Completed | 100% |  |  | tsc --noEmit: 0 errors after fix. All 21 mocks and 1 adapter updated | 2026-08-25 | SubDivision is empty string in mocks (no sub-div level in mock hierarchy)
5 | Bug Fix | DataTable Column header type mismatch | Column interface had header: string but patrols/page.tsx passed JSX elements (sortable headers with icons). Upgraded Column interface header type from string to ReactNode in components/data.tsx. | Shared Components | 0.5h | 2026-08-25 | 2026-08-25 | Completed | 100% |  |  | Fix in components/data.tsx:19. No other components affected | 2026-08-25
6 | Cleanup | Sidebar nav cleanup for patrols | Removed redundant /patrols/all links from sidebar (All Patrols, Ongoing Patrols, Completed Patrols). Consolidated to single 'All Patrols' pointing to /patrols. Removed stale breadcrumb for /patrols/all from nav.ts. | Navigation | 0.5h | 2026-08-25 | 2026-08-25 | Completed | 100% |  |  | nav.ts updated, breadcrumb cleaned. /patrols/all page still exists but unlinked | 2026-08-25 | patrols/all page kept for backward compatibility
7 | DevOps | Environment setup for local development | Created web/.env.local with NEXT_PUBLIC_API_URL=http://localhost:3001. Backend PORT=3001 override. Ran npm install in both web/ and backend/. Installed missing compression dependency after merge. | DevOps | 1h | 2026-08-24 | 2026-08-25 | Completed | 100% |  |  | web/.env.local created, both projects installed clean | 2026-08-25 | Backend on 3001, web on 3000
8 | Feature | Live ranger tracking (real-time position) | Implemented WebSocket-based live ranger position tracking. Backend broadcasts GPS coordinates from mobile app. Frontend displays rangers on map with real-time position updates, trail history, and status indicators. | Rangers / GIS | 8h | 2026-08-24 | 2026-08-24 | Completed | 100% |  |  | Commit a73ebb0: 32 files, +2237/-130 lines | 2026-08-25 | Merged before current session
9 | Bug Fix | MultiPolygon compartment fix | Fixed MultiPolygon geometries not rendering in GIS map view. Updated GeoJSON parsing to handle both Polygon and MultiPolygon geometry types from PostGIS. | GIS Module | 2h | 2026-08-24 | 2026-08-24 | Completed | 100% |  |  | Commit f6fc5a3: +30/-14 lines. 55 compartments with COMP_NO=0 identified | 2026-08-25 | 240 DB rows, 231 Polygon + 9 MultiPolygon
10 | DevOps | Branch management and merge from origin/main | Merged origin/main into Veera branch. Resolved one conflict (trivial formatting in backend-adapters.ts). Fetched 14+ commits from origin/main. | Git | 1h | 2026-08-25 | 2026-08-25 | Completed | 100% |  |  | Merge commit 9efa98f, one conflict resolved trivially | 2026-08-25 | HEAD: 9efa98f on Veera branch
TOTAL |  |  |  |  | 26h |  |  | 10/10 items | 100% avg