## Admin Portal Matrix
NSTR PATROL — ADMIN WEB PORTAL: FULL-STACK COMPLETION MATRIX (audit 2026-08-13 · scope: web frontend + supporting backend APIs · ranger mobile app excluded)
Module / Area | Sub-Item / Functionality | Status | Completion % | Est. Remaining (hrs) | Notes / Remarks
1. Platform Foundation | Project scaffold: Next.js 16 App Router + TypeScript + Tailwind v4 | Completed | 100 | 0 | 33 client pages, zero external UI/chart/map libs
1. Platform Foundation | App shell — sidebar navigation (7 modules, collapse + mobile drawer) | Completed | 100 | 0 | Dashboard, Patrol Ops, Rangers, Observations, GIS, Analytics, Admin
1. Platform Foundation | Scope picker (forest / division / range / beat) | Completed | 100 | 0 | Default: NSTR / d-north / r-n1 / b-n1a
1. Platform Foundation | Global search modal (patrols, rangers, observations, teams) | Completed | 90 | 4 | Mock index (lib/mock/observations.ts searchIndex)
1. Platform Foundation | Notification center + unread badge | Completed | 90 | 4 | 6 mock notifications
1. Platform Foundation | Profile menu + sign-out flow | Partially Complete | 60 | 8 | Toast-only mock; no auth session
1. Platform Foundation | Toast system (success / info / warning / danger) | Completed | 100 | 0
1. Platform Foundation | Design system (Button, Badge, Card, Input, Select, Textarea, Table primitives) | Completed | 100 | 0 | components/ui.tsx + components/data.tsx
1. Platform Foundation | Icon library (~80 inline SVG icons) | Completed | 100 | 0 | components/icons.tsx
1. Platform Foundation | Charts — dependency-free SVG (line, bar, group bars, donut, heatmap, coverage) | Completed | 95 | 4 | components/charts.tsx
1. Platform Foundation | Overlays (Dialog, Drawer, Dropdown, ConfirmDialog, Export, DateRangePicker, Tabs) | Completed | 100 | 0 | components/overlays.tsx
1. Platform Foundation | Loading / error / empty states (skeleton rows, ErrorState, not-found) | Completed | 100 | 0
1. Platform Foundation | Domain types + jurisdiction model (lib/types.ts) | Completed | 100 | 0 | PatrolAuthorization, JurisdictionState, audit events
1. Platform Foundation | Services data layer (lib/services.ts — single mock repository, simulated latency) | Completed | 95 | 4 | Swap point to real backend API
1. Platform Foundation | App context store (scope, toasts, export dialog) | Completed | 100 | 0
1. Platform Foundation | Breadcrumbs + PageHeader pattern across all pages | Completed | 100 | 0
1. Platform Foundation | Auth / session — replace hardcoded super-admin with JWT login | Partially Complete | 30 | 24 | CURRENT_ROLE constant in permissions pages; no login page
1. Platform Foundation | Role-based access control (super-admin / senior officer / read-only) | Not Started | 0 | 16 | Permission matrix exists in admin UI only
1. Platform Foundation | Shell unit/integration tests | Not Started | 0 | 24 | No test framework in web/
2. Dashboard | KPI row — active patrols, normal today, authorized today, incidents, rangers on duty, coverage | Completed | 95 | 4 | KPI links deep-link into filtered lists
2. Dashboard | GIS overview panel | Partially Complete | 80 | 12 | Mock SVG map; real MapLibre planned
2. Dashboard | Patrol status donut + legend | Completed | 100 | 0
2. Dashboard | Alerts feed (critical / warning / info) | Completed | 90 | 4 | Mock notifications
2. Dashboard | Today's activity line chart (patrols + reports by hour) | Completed | 100 | 0
2. Dashboard | Forest hierarchy distribution cards | Completed | 95 | 4 | Patrol/coverage/ranger figures hardcoded
2. Dashboard | Today's incidents + recent reports lists | Completed | 95 | 4 | Mock observations
2. Dashboard | Today's patrols list | Completed | 100 | 0
2. Dashboard | Zero patrol zones card | Completed | 100 | 0 | Mock zones (b-c1b, b-s1b, b-n2b)
2. Dashboard | Patrol heatmap preview | Completed | 100 | 0
2. Dashboard | Quick actions grid | Completed | 100 | 0 | Includes Patrol Permissions entry
2. Dashboard | Live refresh (60s polling) | Partially Complete | 50 | 6 | Refresh button shows mock toast only
2. Dashboard | Wire dashboard to backend (patrols + analytics APIs) | Not Started | 0 | 32
3. Patrol Operations | Patrol dashboard (§6.1) — KPIs, status donut, exceptional patrols, active authorizations, recent completed | Completed | 95 | 4 | Read-only monitoring per new operating model
3. Patrol Operations | All patrols (§6.2) — sortable DataTable + pagination | Completed | 100 | 0
3. Patrol Operations | All patrols — filter bar (status, jurisdiction, type, method, division, range, beat, ranger, date range, query) | Completed | 95 | 4
3. Patrol Operations | Jurisdiction badges — normal / authorized exception / pending review / requires review | Completed | 100 | 0 | components/jurisdiction.tsx
3. Patrol Operations | Table / card view switcher | Completed | 100 | 0
3. Patrol Operations | Patrol details (§6.3) — summary, jurisdiction banner, events timeline, coverage, notes | Completed | 95 | 4 | Read-only from admin perspective
3. Patrol Operations | Patrol details — export dialog | Completed | 100 | 0
3. Patrol Operations | Patrol history — grouped by day with jurisdiction status | Completed | 85 | 6
3. Patrol Operations | Patrol reports list + export | Partially Complete | 70 | 12 | Header flags: wire to backend reports endpoint
3. Patrol Operations | Route replay — spatial timeline playback | Completed | 90 | 6 | Timed points on mock map
3. Patrol Operations | Not-found handling for unknown patrol ids | Completed | 100 | 0
3. Patrol Operations | Backend — patrol list / get / history APIs | Not Started | 0 | 32 | Sync data from mobile; telemetry aggregates exist in schema
3. Patrol Operations | Backend — reports + export endpoints | Not Started | 0 | 16
4. Patrol Permissions | Workspace list — status / priority / type filters, table, pagination, export | Completed | 95 | 4 | §6 — exception-authorization management
4. Patrol Permissions | Workspace — approve / revoke actions with confirm dialogs | Completed | 95 | 4 | Role-gated (super-admin)
4. Patrol Permissions | Create authorization wizard — step 1: ranger select with normal jurisdiction | Completed | 100 | 0
4. Patrol Permissions | Create wizard — step 2: authorized area (GIS map pick + division/range/beat selects, same-area warning) | Completed | 100 | 0 | AuthAreaMap interactive
4. Patrol Permissions | Create wizard — step 3: details (reason, instruction, patrol type, validity, priority, restrictions) with field-level validation | Completed | 95 | 4 | Parsed-date validation + auto-extend validity
4. Patrol Permissions | Create wizard — step 4: review summary + area preview map | Completed | 100 | 0
4. Patrol Permissions | Create wizard — step 5: approve (active) or save draft | Completed | 100 | 0
4. Patrol Permissions | Authorization details — audit history timeline (create → approve → used → revoke/expire) | Completed | 100 | 0 | §6.17–19
4. Patrol Permissions | Authorization details — related patrols table with view / replay | Completed | 100 | 0
4. Patrol Permissions | Authorization details — normal vs authorized jurisdiction compare + GIS map | Completed | 100 | 0
4. Patrol Permissions | Jurisdiction validation engine (resolveJurisdiction) across patrols, rangers, permissions | Completed | 100 | 0 | lib/jurisdiction.ts
4. Patrol Permissions | Backend — authorization CRUD + approve / revoke + audit trail APIs | Not Started | 0 | 40 | No authz model in Prisma schema yet
4. Patrol Permissions | Backend — authorization ↔ patrol linkage (validate patrols under auth) | Not Started | 0 | 12
5. Ranger Management | Directory (§7.1) — cards/table, search, duty-status filters | Completed | 95 | 4
5. Ranger Management | Profile (§7.2) — header stats, performance trend chart | Completed | 95 | 4 | Monthly patrols + coverage (mock)
5. Ranger Management | Profile — coverage vs beat target progress | Completed | 100 | 0
5. Ranger Management | Profile — current patrol live card | Completed | 95 | 4 | Mock live status
5. Ranger Management | Profile — recent patrols with jurisdiction badges | Completed | 100 | 0
5. Ranger Management | Profile — normal jurisdiction + authorized exceptions cards (active/expired auths, cross-jurisdiction patrols) | Completed | 100 | 0 | §7.2 extension
5. Ranger Management | Profile — issued equipment + recent activity timeline | Completed | 100 | 0
5. Ranger Management | Ranger onboarding (rangers/new) | Partially Complete | 80 | 8 | Mock submit → toast + redirect
5. Ranger Management | Teams (§7.3) — roster grouping | Completed | 85 | 8 | Mock teams
5. Ranger Management | Vehicles (§7.4) | Completed | 85 | 8 | Mock records
5. Ranger Management | Weapons (§7.5) | Completed | 85 | 8 | Mock records
5. Ranger Management | Equipment (§7.6) | Completed | 85 | 8 | Mock records
5. Ranger Management | Backend — rangers / teams / vehicles / weapons / equipment APIs | Not Started | 0 | 40
6. Observations & Reports | Dashboard (§8.1) — category mix, severity distribution, review pipeline | Completed | 95 | 4
6. Observations & Reports | List (§8.2) — searchable table with filters | Completed | 100 | 0
6. Observations & Reports | Detail (§8.3) — media, attributes, resolve / escalate workflow | Partially Complete | 80 | 8 | Workflow is mock-only
6. Observations & Reports | Backend — observations CRUD + workflow API | Not Started | 0 | 32 | Incident model exists in Prisma
6. Observations & Reports | Backend — photo upload/serving (MinIO) | Not Started | 0 | 16
7. GIS Intelligence | Workspace — layer manager (basemap / activity / analysis, 12 layers) | Completed | 100 | 0 | Mock SVG map (viewBox 1000×700)
7. GIS Intelligence | Markers — rangers, observations, incidents, SOS | Completed | 100 | 0
7. GIS Intelligence | Route playback | Completed | 100 | 0
7. GIS Intelligence | Zero-patrol-zone board | Completed | 100 | 0
7. GIS Intelligence | Patrol authorization areas layer (active auth beats) | Completed | 100 | 0 | Added with Permissions module
7. GIS Intelligence | Coverage tint + activity heatmap layers | Completed | 100 | 0
7. GIS Intelligence | Real map engine (MapLibre GL / vector tiles) | Not Started | 0 | 32 | Current map is frontend-only mock SVG
7. GIS Intelligence | Backend — GIS data APIs (forests, boundaries, grids, geo queries) | Not Started | 0 | 24 | ForestBoundary/ForestGrid models exist
8. Analytics & Insights | Forest view — KPI series + scope tabs (forest/division/range/beat) | Completed | 100 | 0
8. Analytics & Insights | Weekly patrols & observations (group bars) | Completed | 100 | 0
8. Analytics & Insights | Monthly coverage trend | Completed | 100 | 0
8. Analytics & Insights | Human impact trend | Completed | 100 | 0
8. Analytics & Insights | Water body status | Completed | 100 | 0
8. Analytics & Insights | Animal mortality trend | Completed | 100 | 0
8. Analytics & Insights | Wildlife sightings mix | Completed | 100 | 0
8. Analytics & Insights | Beat coverage bars | Completed | 100 | 0
8. Analytics & Insights | Patrol activity heatmap grid | Completed | 100 | 0
8. Analytics & Insights | Jurisdiction compliance donut + KPIs (normal / authorized / pending / out-of-authorization) | Completed | 100 | 0
8. Analytics & Insights | Leaderboards — rangers / beats / ranges / divisions (§10.4–10.7) | Completed | 85 | 8
8. Analytics & Insights | Export (CSV-like dialog) | Completed | 100 | 0
8. Analytics & Insights | Backend — analytics / KPI / trend APIs | Not Started | 0 | 40
9. Administration | Governance overview (§11.1) | Completed | 85 | 8
9. Administration | Users (§11.2) — list, status, invite dialog | Partially Complete | 80 | 8 | Invite is mock toast
9. Administration | Roles (§11.3) — role cards + permission matrix (5 roles × 7 modules) | Completed | 85 | 8
9. Administration | Master data (§11.4) — 7 tabs (species, categories, water types, patrol types/objectives, vehicle/weapon) | Partially Complete | 60 | 16 | Add/edit shows '(planned)' toast
9. Administration | Audit logs (§11.5) — immutable trail | Partially Complete | 70 | 12 | Mock data; header flags mock
9. Administration | Settings (§11.6) — thresholds + notification templates | Partially Complete | 70 | 12 | Save is mock only
9. Administration | Backend — users / roles / invite APIs | Not Started | 0 | 24 | User model exists
9. Administration | Backend — master data CRUD API | Not Started | 0 | 24
9. Administration | Backend — audit log API (append-only) | Not Started | 0 | 16
9. Administration | Backend — settings + notification templates API | Not Started | 0 | 16
9. Administration | Backend — notification delivery (email/push) | Not Started | 0 | 24
10. Integration & Delivery | Swap mock services for authenticated API calls across all modules | Not Started | 0 | 80 | Services layer ready as swap point
10. Integration & Delivery | API error / validation mapping (ZodError → 400 contract) | Partially Complete | 40 | 16 | Backend error middleware exists; frontend mapping pending
10. Integration & Delivery | Auth session persistence + token refresh | Not Started | 0 | 16
10. Integration & Delivery | Real-time patrol updates (polling / SSE / WebSocket) | Not Started | 0 | 20
10. Integration & Delivery | Observation photo serving + preview | Not Started | 0 | 12
10. Integration & Delivery | Frontend unit tests (Vitest + Testing Library) | Not Started | 0 | 32
10. Integration & Delivery | E2E tests (Playwright) for critical flows (login, patrols, permissions) | Not Started | 0 | 32
10. Integration & Delivery | CI — web workflow + lint/typecheck gate | Completed | 100 | 0 | .github/workflows/web.yml
10. Integration & Delivery | Deployment — Next standalone / Docker + env config | Partially Complete | 40 | 12 | docker-compose covers backend infra only
10. Integration & Delivery | Production hardening (rate limits, audit, RBAC enforcement, secrets) | Not Started | 0 | 24
10. Integration & Delivery | PRD ↔ implementation traceability documentation | Partially Complete | 60 | 8 | Page headers cite PRD sections already
TOTAL | 119 sub-items · average completion 73% |  |  | 978 | Estimated remaining effort, full admin-portal stack (frontend + backend APIs + QA)

## Summary
NSTR Patrol — Admin Web Portal: Module Summary
Module / Area | Sub-items | Avg Completion % | Est. Remaining (hrs)
1. Platform Foundation | 19 | 82 | 88
10. Integration & Delivery | 11 | 22 | 252
2. Dashboard | 13 | 85 | 66
3. Patrol Operations | 13 | 79 | 84
4. Patrol Permissions | 13 | 83 | 64
5. Ranger Management | 13 | 85 | 92
6. Observations & Reports | 5 | 55 | 60
7. GIS Intelligence | 8 | 75 | 56
8. Analytics & Insights | 13 | 91 | 48
9. Administration | 11 | 41 | 168
GRAND TOTAL | 119 | 73% | 978